## README
Last Update | 2018-10-03
Author | Edward Zabrensky,
Email | ezabr001@ucr.edu
Description | This is a SCRUM template designed for project managment in CS180. Replace this section with YOUR TEAM information
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: On/Off (Edward Zabrensky)
Task 2: Search bar(Ed, Marcos)
Task3:Settings (Marcos)
Task4: history (Moker)
Task5: Compare (Eric)
Task 6: Visual Indicator (Moker)
Task 7 : Price History (Eric)
Task 8 : Review
Task 9: Review Legitmacy
Task 10: Creating a clickable button
Task 10: find similar items

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | On/Off | As a user, I want to turn on or turn off Cheaper on Amazon, so that I can disable the extension withoutremoving it from Chrome | 2 | 1
1 | Search | As a user, I want the extension to search for the product that I am looking at on Amazon, so I can find the cheaperdeal. | 4 | 2
2 | Compare | ​​As a user, I want the extension to compare and identify the cheaper product between thecurrent website and Amazon if it exists. | 4 | 5
4 | Visual Indicator | As a user, i want the Chrome extension icon to turn green if the product is cheaper on Amazonand red if it is not, so that I can easily see if it is cheaper or not. | 2 | 6
3 | History | As a user, I want to view the last 10 products that I searched for, so that I can remember what Iwanted. | 4 | 4 | This is saving price history search history until product linking/search is complete
6 | Reviews | As a user, I want to view Amazon reviews of the product I am browsing, I want to do this bylooking at the statistics of the items, so that I can determine if it is a product worth buying by looking at whatothers have thought of the product. | 8 | 8 | only implement if have time
5 | Review Legitamacy | As a user, I want to be able to see the legitimacy of the Amazon reviews I am looking at todetermine if the product has a significant number of trustworthy reviews. | 8 | 9 | only implement if have time
8 | Price History | As a user, I want to view the price history of the product I am searching, so that I can feelmore confident that I am getting the product for the best price when buying the item. | 4 | 7
9 | Settings | As a user, I want to turn on/off certain features of the extension, so that I can personalize the extensionto my needs. | 4 | 3
| Total |  | 36

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Edward Zabrenky | On/off, setting,price history, history
2 | Marcos Miranda | Search, review legitamacy, find similar items, inject button
3 | Erik | -

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 36 | 0 | 0 | 36 | 36
1 | 36 | 14 | 14 | 22 | 30.625
2 | 36 | 12 | 26 | 10 | 26.25
3 | 36 | 0 | 26 | 10 | 21.875
4 | 36 | 0 | 26 | 10 | 17.5
5 | 36 | 0 | 26 | 10 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0